## SprintBacklog
SPRINT 1 BACKLOG
[7 empty] | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-09-03 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-09 | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-13
ID | User Story | Tasks | Owner | Status | User Story estimated efffort | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1 | As a User, when I login, I want to be able to differentiate if my account is a regular user account or an administrator account | When I login, I should see that the system welcomes me as a User or Administrator. | Milni | Complete | 16 | 8
|  | When this is displayed, the access that I am given should be identical to said role. |  |  |  | 8
| As any user logging in, I want my password to be encrypted to minimise any security concerns | When I enter my new password into the login section, the text should be hidden. | Milni | Complete | 13 | 8
|  | Passwords must not be transmitted in plain text during the registration or login process. |  |  |  | 5
2 | As a User, if I come across any errors or input any incorrect data whilst logging in, I wish to be presented with a legible and simple error message | When I enter the wrong password, the system should notify that my password is incorrect. | Milni | Complete | 18 | 4
|  | When I enter the wrong password, the system should not allow me to access anything. |  |  |  | 6
|  | When this error is produced, it should be clear to me that I have entered the wrong data. |  |  |  | 4
|  | When this error is produced, it should be legible, grammatically correct, and coloured red. |  |  |  | 4
3 | As a User, I wish to be able to drag and drop the tasks added to the system between each of the columns. | When I click on a task and drag it to a new lane, it should successfully land in that new lane. | Carissa | Incomplete/In Progress | 24 | 7
|  | When I move the task over to the new lane, it should not exist in the previous lane. |  |  |  | 5
|  | When I move a task over to a new lane, the contents within said task should remain the same. |  |  |  | 6
|  | When the task is successfully moved into the new lane, I should be able to move it again if I wanted. |  |  |  | 6
4 | As a User, I wish to be able to access a page where I can edit my password | When I want to edit my password, I should be able to press a button that opens a new window or page to change my password | Kirtan | Incomplete/In Progress | 26 | 8
|  | When I enter my new password into said page or window input, the text should be hidden. |  |  |  | 8
|  | When I successfully enter my password and click change, it should prompt me that my change has been successful. |  |  |  | 4
|  | When I enter a password that is the same as my previous one, the system should deny my change. |  |  |  | 6
5 | As an Administrator, I wish to be able to access content from anywhere, and have it editable by anyone else so the changes are synced across different sessions | When I view the list of tasks, it should display dynamically based on the database. | Nilly | Complete | 20 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 0 | 3
|  | When I add a task to the database, it should be able to be placed directly into Doing or Done, not just To-do. |  |  |  | 3
|  | When a different user accesses the system, they should be able to view my changes. |  |  |  | 6
|  | When I add a task, it should also be added to the database. |  | Incomplete/In Progress |  | 9
| As a User, if I am unsure about how to navigate the system, I wish to be able to navigate to the instructions page and view the directions of use | When I land upon logging in, I should be able to see an Instructions box in the nav bar. | Max | Incomplete/In Progress | 15 | 3
|  | When I press this button, I should be led to either a new page or a pop-up window. |  |  |  | 3
|  | When this pop-up window or page opens, it should display a series of texts detailing how to use the system. |  |  |  | 4
|  | Upon reading the text, it should be legible and grammatically correct, clear and concise. |  |  |  | 5
6 | As a User, I wish to be able to colour code my tasks so that they can be separated into different categories | When I am creating or editing a task, I should be able to assign a colour to that task. | Erin | Complete | 15 | 4
|  | When I am selecting from the list of colours, there should either be a preset list of colours or support for any HEX colour code. |  |  |  | 3
|  | When I select my desired colour, that colour should be reflected somewhere on the task. |  |  |  | 3
|  | When I access the system at another time or location, that colour should retain there. |  | Incomplete/In Progress |  | 5
7 | As an Administrator, I wish to be able to view the hours spent or planned to be allocated on each task, in an analytical graph format | When I view the hours spent on allocated tasks, there should be a graph that showcases the hours of each team member or task. | Chaitsee | Incomplete/In Progress | 12 | 2
|  | When I want to add more hours to a task, the graph should reflect those changes. |  |  |  | 7
|  | When I am looking at the graph, it should clearly differentiate between each member and or task. |  |  |  | 3
Total |  |  |  |  | 159 | 159 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 0 | 3

## Burndown chart
Dates | Estimated Efforts
1 | 110
2 | 109
3 | 102
4 | 94
5 | 75
6 | 58
7 | 52
8 | 43
9 | 35
10 | 28
11 | 24
12 | 24
13 | 20
14 | 20
Sprint Velocity: -7.25*x + 327582