## Sheet1
PRODUCT BACKLOG REPORT
ID | USER Priority | User Stories | Tasks | TASK Priority | SPRINT NO | STATUS | STATUS | PRIORITY
1 | High | As an employee, I want to be able to view a system that looks aesthetically satisfying, so the system is user friendly | The system's interface should be aesthetically pleasing and user-friendly. | 1 | 1 | Complete | Not Started | High
|  |  | Menus and buttons need clear labels and logical placement. | 2 |  |  | In Progress | Medium
|  |  | Content should be organized with proper spacing and readability. | 3 |  |  | Complete | Low
|  |  | Error messages should be user-friendly and informative. | 4 |  |  | Overdue
2 | High | As a user of the system, I want to be able to add tasks based on the text I enter within an entry box, so I can label what I am adding | The task entry box must be prominently displayed and easily accessible. | 1 | 1 | Complete | On Hold/Suspended*
|  |  | Pressing "Add" or Enter should create a new task as entered. | 2
|  |  | Tasks in the list must clearly display the entered text. | 3
|  |  | Tasks should appear in the order added for easy management. | 4
3 | High | As a user of the system, I want to be able to check tasks off when they are considered complete, so others can see that they are complete | Task lists must offer a clear way, like checkboxes, to mark tasks complete. | 1 | 1 | Complete
|  |  | Checking the box should visually indicate completion, like striking through the text. | 2
|  |  | Others accessing the list should see the task marked as complete. | 3
|  |  | Unchecking the box should return the task to its original state. | 4
4 | High | As a user of the system, I want to be able to move tasks up and down their respective list to showcase priority, so other users can see which tasks must be complete first | Task lists must allow easy task reordering for changing priority. | 1 | 1 | Complete | *Renegotiated as requirement after discussion with PO
|  |  | Initiating task movement should use a clear and intuitive dragging mechanism. | 2
|  |  | After saving changes, the new order should persist for all users. | 3
|  |  | Tasks should display in priority order, with the most important ones at the top. | 4
5 | High | As an employee, I want to be able to login to the system with details that are provided to me, so I can login and access the system | The login page should offer fields for entering username and password. | 1 | 1 | Complete
|  |  | Clicking "Login" should authenticate and grant access upon success. | 2
|  |  | Unsuccessful logins should display clear error messages for identification. | 3
|  |  | Secure session storage should keep me logged in or until I log out or it expires. | 4
6 | Medium | As a product user, I want to be able to move tasks from "To Do" to "Doing" to "Done", so I can properly label each task | Transitioning tasks from "To Do" to "Doing" should be intuitive. | 1 | 2 | Complete
|  |  | Initiating movement shifts tasks from "To Do" to "Doing" category. | 2
|  |  | Initiating movement shifts tasks from "Doing" to "Done" category. | 3
|  |  | Task movements visually reflect progress and completion in categories. | 4
7 | Medium | As an employee, I want my work to be able to edit tasks as requirements change so I know I am not locked in to the original task. | Modify Tasks | 1 | 2 | Complete
|  |  | Save Previous Tasks | 2 |  | Complete
|  |  | Sync changes to all users | 3 |  | Incomplete
8 | Medium | As a team leader, I want to be able to assign my colleagues to specific tasks so that the entire team can know who's in charge of what. | Have different user roles in the system |  | 2 | On Hold
|  |  | Assign users specific tasks |  |  | Complete
Sync task assignment across all users
Notify users when given a task
Users can't modify the tasks they have been assigned
9 | Low | As an employee, I want to be able to tag the tasks under specific categories so that it will be clearer what the task entails/ which part of the project the task is for. | Add tags/categories | 1 | 2 | Complete
|  |  | Modify tags/categories | 3
|  |  | Allocate tags to tasks | 2
|  |  | Remove tags | 4
10 | Low | As an admin, I want to see how much time, averaging over the number of productive days, each person has spent on the project. | Users need to be able to input time spent on their tasks daily |  | 3 | On Hold
Store the user time data
Make the user time data available for admin users to oversee
Plot the user data against time
11 | Low | As an admin, I want to be able to change the date range that the charts are shown over. | Save charts for a given range of dates |  | 3 | On Hold
Allow admin user to select the date range
Select the chart in that date range
12 | Low | As an admin, I want to be able to add users to the project. | Login as administrator |  | 3 | Complete
Add users to system
Ensure new users can login
TOTAL