## SprintBacklog
SPRINT 3 BACKLOG
|  |  | KEY HERE |  |  |  |  | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19
ID | User Story | Tasks | Priority | Owner | Status | User Story estimated efffort | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1 | As a Developer, I want to be able to see motivational messages whilst working on and finishing my tasks so that I can feel inspired | When I click on the "Motivational Message" button, an inspiring message pops up onto the screen |  | Milni + Carissa | Completed | 7 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | When I cross off a task as done, a randomised encouraging message pops up onto the screen |  |  |  |  | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | As a Project Manager, I want to be able to view past sprints so that I can check the progress of each sprint | When a new sprint has been created, a new tab should dynamically be created on the past sprints page |  | Nilly | Completed | 17 | 8 | 8 | 7 | 6 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  | When I click on the past sprints page, I should be able to choose a sprint and display all categories (Done, To do, Doing) as well as the task assignee |  |  |  |  | 9 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0
3 | As a Developer, I wish to be able to drag and drop the tasks added to the system between each of the columns. | When I click on a task and drag it to a new lane, it should successfully land in that new lane. |  | Carissa | Complete | 22 | 7 | 7 | 7 | 6 | 5 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | When I move the task over to the new lane, it should not exist in the previous lane. |  |  |  |  | 7 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | When I move a task over to a new lane, the contents within said task should remain the same. |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | When the task is successfully moved into the new lane, I should be able to move it again if I wanted. |  |  |  |  | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | As a User, I wish to be able to access a page where I can edit my password | When I update my password, I would like to see a user friendly interface |  | Kirtan | Complete | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | As a User, if I am unsure about how to navigate the system, I wish to be able to navigate to the instructions page and view the directions of use | When I press the instructions page on the drop down menu, I should be led to a new page |  | Max | Complete | 10 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upon reading the text, it should be legible and grammatically correct, clear and concise.
6 | As a Scrum Master, I want to be able to set assignees to tasks and also be able to edit them so that the team understands what task they should be doing | When I add a new task, I should also be prompted to add an assignee |  | Erin | Complete | 7 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | When I want to update existing tasks (name and task itself), I should be able to easily edit the details |  |  |  |  | 4 | 4 | 3 | 2 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
7 | As an Administrator, I wish to be able to view the hours spent or planned to be allocated on each task, in an analytical graph format so that the team progress is tracked | When I view the hours spent on allocated tasks, there should be a graph that showcases the burndown chart |  | Chaitsee + Milni | Complete | 23 | 9 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
|  | When I want to add more hours to a task, the graph should reflect those changes. |  |  |  |  | 5 | 5 | 5 | 4 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  | When I am looking at the graph, I should be able to see the correct dates of each sprint |  |  |  |  | 9 | 9 | 9 | 8 | 7 | 6 | 5 | 5 | 4 | 3 | 3 | 2 | 1 | 0 | 0
Total | [5 empty] | 89 | 89 | 89 | 77 | 62 | 49 | 35 | 24 | 19 | 18 | 8 | 5 | 3 | 1 | 0 | 0
Sprint Velocity: -6.76*x + 78.5 |  |  | Priority Burndown
|  |  |  | 7 |  | 7 = Immediate Priority
|  |  |  | 6 |  | 6 = Product Must have. Immediate client requirement
|  |  |  | 5 |  | 5 = Product Must have. Client requirement
|  |  |  | 4 |  | 4 = Minimum Viable Product. Product Must have
|  |  |  | 3 |  | 3 = Product will function better with, but can be missed
|  |  |  | 2 |  | 2 = Would be good to have, but can skip if time does not allow
|  |  |  | 1 |  | 1 = Product can have, only if time allows

## Burndown chart
Dates | Estimated Efforts
1 | 89
2 | 77
3 | 62
4 | 49
5 | 35
6 | 24
7 | 19
8 | 18
9 | 8
10 | 5
11 | 3
12 | 1
13 | 0
14 | 0
Sprint Velocity: -6.76*x + 78.5